Budget

| Staff Costs: |  |  |  |
| --- | --- | --- | --- |
| Role | Hourly Rate | Number of hours assigned | Total |
| Workshop Facilitator for Joy in Numbers | £100 | 12 | £1,200 |
| Workshop Facilitator for Skipton HS HAZ Launch | £100 | 4 | £400 |
| Freelance Artist for Cultural Programme Community Consultation Artwork | £20 | 25 | £500 |
| Freelance Artist for Skipton HS HAZ Brand Development | £20 | 40 | £800 |
| Freelance Artist for Skipton HS HAZ Launch | £20 | 30 | £600 |
|  |  | Total Staff Costs | £3,500 |

| Non-staff costs: |  |  |  |
| --- | --- | --- | --- |
| Description | Cost | Quantity | Total |
| Workshop Materials for Joy in Numbers | £5 | 120 | £600 |
| Materials for Cultural Programme Community Consultation Days | £100 | 2 | £200 |
| Workshop Materials for Skipton HS HAZ Launch | £5 | 40 | £200 |
| Venue hire for Joy in Numbers Workshops | £50 | 6 | £300 |
| Venue Hire for Skipton HS HAZ Launch Workshops | £50 | 2 | £100 |
| Printing of Skipton HS HAZ Launch Artworks onto vinyl wraps | £400 | 3 | £1,200 |
| Marketing on Social Media | £40 | 25 | £1,000 |
| Contingency at 10% |  |  | £700 |
|  |  | Total Non-staff Costs | £4,300 |

| In-kind Contributions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Name of Contributor |  | Status | Amount |
| Venue Hire for Meetings | Craven College |  | Confirmed | £500 |
| Venue Hire for Cultural Programme Community Consultation Days | Craven Court |  | Pending | £1,000 |
| Equipment for Workshops | Fresh Perspective |  | Confirmed | £600 |
|  |  | Total In-Kind Contributions |  | £2,100 |

| Volunteer Contributions |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Skills Set | Type of Work |  | No. of Volunteers |  |  | Hourly Rate | No. of Hours | Total |
| Skilled Labour | Project Leads |  | 2 |  |  | £20 | 50 | £2,000 |
| Skilled Labour | Workshop Assistants |  | 6 |  |  | £20 | 16 | £1,920 |
| Skilled Labour | Street Performers for Consultation Days |  | 4 |  |  | £20 | 14 | £1,120 |
| Unskilled Labour | Marshals for Consultation Days |  | 6 |  |  | £10 | 14 | £840 |
| Skilled Labour | Research Assistants for Activities |  | 4 |  |  | £20 | 10 | £800 |
|  |  |  |  |  | Total Volunteer Contributions |  |  | £4,760 |